## Issues
Toward v1.0 change tracker
Only one item may be Approved or Implemented at a time. New ideas may remain queued without interrupting the active contract.
Open items |  |  | Active items |  |  | Closed items
ID | Item | Area | Status | Opened | Closed | Reason | Change boundary | Next step | Depends on | Evidence
ARC-178A-001 | Remove cross-version COM and COMStatus inheritance | Architecture / P2 | Closed | 2026-10-18 | 2026-10-19 | 178A currently inherits 93A orchestration and status behavior, exposing stale fields and methods. | Make 178A COM and COMStatus standalone. Preserve equations, config mapping, search behavior, reporting values, and public numerical results. | Closed. Continue with ARC-178A-002 after review. |  | Commit cc5339e; fixed-case numerical state exact; 140 tests + 2 subtests passed; 4-candidate search smoke passed; 47 report plots and hashes verified.
ARC-178A-002 | Semantic dataclass text representation | Reporting / P4 / P7 | Closed | 2026-10-18 | 2026-10-22 | Generic _PrettyDataclass output does not express semantic order, units, stage state, or bounded array summaries. | Add explicit to_string(), print(), __str__(), and concise __repr__() contracts. Dataclasses describe content; report workflow owns files. | Closed. Continue with ARC-178A-003 after review. | ARC-178A-001 | Commit 149bbd6; fixed-case numerical state exact; 147 tests and 2 subtests passed; 12 focused semantic-text/search/reporting tests passed.
ARC-178A-003 | Unified 93A and 178A COMReport mapping and plots | Reporting / P7 | Closed | 2026-10-18 | 2026-10-23 | Version reporters should share plotting behavior while accepting version-specific config and status trees. | Use shallow canonical stage mapping and shared plot_<stage>() methods. Do not recompute model quantities inside reporting. | Closed. Continue with the queued 93A golden-case schema migration after review. | ARC-178A-002 | Commit e5b0b2b; 93A/178A report generation preserved all checked COM values exactly; 32/53 PNG files and manifest hashes verified; 152 tests + 2 subtests passed.
GOV-V1-001 | Track toward v1.0 changes in one workbook | Governance / P8 | Closed | 2026-10-18 | 2026-10-18 | New ideas need a durable place without forcing immediate implementation or losing the active modification boundary. | Maintain one concise tracker with one active contract. Record queued ideas, dependencies, open and close dates, and closure evidence. | Maintain the tracker as new v1.0 issues are raised and close active items only after verification. |  | docs/planning/open_issues.xlsx; AGENTS.md
ARC-CROSS-001 | Create a runnable current-schema 93A golden case | Validation / 93A | Open | 2026-10-23 |  | Every checked-in 93A workbook currently fails the current parser because required field names have drifted, so production-path 93A golden validation is unavailable. | Migrate or add one maintained 93A workbook and numerical baseline. Do not change 93A equations or silently rewrite legacy workbooks. | Prepare the ARC-CROSS-001 contract: choose the canonical source case, enumerate schema migration fields, and define the numerical baseline. | GOV-V1-002 | ARC-178A-003 parser audit: C2M workbooks miss R_0; case_260915_report misses txpkg_victim.gamma_0; template has no enabled victim.
ARC-REPORT-001 | Review and refine cross-version report plots | Reporting / P7 | Open | 2026-10-23 |  | User review found presentation issues in the generated 93A/178A plots after the shared reporting architecture was completed. | Collect exact plot-level issues first, then change shared renderers or version composition under a separate approved contract. Do not change COM algorithms or status data to improve presentation. | Collect exact plot-level issues and complete the reporting contract before v1.0 G9 is closed. | ARC-178A-003 | User review on 2026-10-23; regenerated 93A/178A report inventory contains 30 shared plot slots, 2 93A-only plots, and 23 178A-only plots.
ARC-178A-004 | Decouple 178A from 93A implementation ownership | Architecture / P2 | Closed | 2026-10-23 | 2026-10-25 | 178A currently aliases seven 93A types, subclasses three 93A classes, and directly calls four 93A private helpers, so the 178A algorithm and data-flow implementation still depends on the 93A module. | Remove every 178A-to-93A dependency edge. Both versions may depend on neutral parents, contracts, and pure shared primitives, while each version retains its own concrete algorithm orchestration and semantic types. | Closed. 178A architecture review may proceed without a 93A implementation dependency. | ARC-178A-001 | Commits 4e21aca, 313cf6b, 13d1018, and 40470e8; architecture dependency ratchets and 178A golden regressions passed.
UTIL-SNP-001 | Preserve explicit S2P and S4P representations | Utility / S-parameter / P6 | Closed | 2026-10-27 | 2026-10-27 | Raw S4P information and Sdd conversion provenance must remain explicit. | Add copy-returning S2P/S4P representation operations and explicit COM ingestion conversion; preserve 93A/178A results. | Closed. | ARC-178A-004 | Commit d9a2c6e; S-parameter round-trip, channel, 93A/178A golden, and regression tests passed.
UTIL-EYE-001 | Add deterministic LinkSegment eye plotting | Utility / sampled response / P6 | Closed | 2026-10-27 | 2026-10-27 | Circuit studies need a reusable SBR-to-eye utility without adding COM-specific CDR or noise behavior. | Add deterministic eye_traces() and presentation-only plot_eye(); caller supplies symbols and transient discard. | Closed. | UTIL-SNP-001 | Commit e7e1612; 12 focused tests, 93A/178A golden checks, and full regression passed.
COMPAT-PY37-001 | Update the Python 3.7 utility export | Compatibility / utility | Closed | 2026-10-27 | 2026-10-27 | The standalone compatibility artifact must expose the maintained utility behavior under exact CPython 3.7.3. | Regenerate and validate the compatibility export without changing COM production behavior. | Closed. | UTIL-EYE-001 | Commit f774487; exact CPython 3.7.3 compatibility validation passed.
UTIL-SNP-002 | Define target semantics for synthetic S4P export | Utility / S-parameter / P6 | Closed | 2026-10-27 | 2026-10-27 | Export impedance and reader port order must describe the desired external file contract rather than the source representation. | Renormalize to target differential impedance and apply the inverse reader permutation before Touchstone export. | Closed. | UTIL-SNP-001 | Commit 94e5613; multiple port-order/impedance round trips and Python 3.7 validation passed.
GOV-V1-002 | Close the 178A design review and reconcile v1.0 status | Governance / P8 / P9 | Closed | 2026-10-27 | 2026-10-27 | Implemented work, tracker state, design-review status, and release gates diverged before utility work began. | Reconcile AGENTS workflow rules, 178A design review, active contracts, tracker, validation index, and release gate. No model changes. | Closed. ARC-CROSS-001 is the next proposed contract. | ARC-178A-004, UTIL-SNP-002 | docs/models/178A/design_review.md; docs/planning/active_contracts.md; docs/operations/v1_0_release_gate.md; governance closure commit.